## Overview
School ERP development progress
296 screens across 25 modules. Counts update when the team edits the tracker. | [6 empty] | Review date
Screens in scope |  |  | No owner |  |  |  | Baseline: mockups are ready. Implementation, owners and deadlines have not been assessed.
Mockups ready |  |  | No deadline
Development verified |  |  | Blocked
Released |  |  | Overdue |  |  |  | Completion measures verified screens, not hours or effort. Shared services are tracked separately. This workbook is updated manually.
Verified completion rate |  |  | Due within 7 days
Not assessed |  |  | Release needs review
Shared tasks verified |  |  | Rework / rolled back
Filter Screen Tracker by owner, sprint, module or state. Enter zero open critical/high bugs only after checking.
Progress by module
Module | Screens | Frontend done | API resolved | Integrated | QA passed | Dev verified | Released | Blocked | Overdue
Public Website & Authentication
Super Admin / SaaS Administration
Organization / School / Branch Setup
Role Dashboards
Admissions & Enquiries
Students
Parents & Guardians
Teachers & Staff
Academics & Curriculum
Student Attendance
Timetable & Substitution
Homework & Assignments
Examinations / Marks / Results
Fees & Finance
HR / Leave / Payroll
Transport / Bus / GPS
Library
Hostel
Health / Counselling / Discipline
Visitor / Gate / Security
Inventory / Assets / Labs
Events / PTM / Communication
Documents & Certificates
Reports & Analytics
Settings / Roles / Permissions / Audit
Total
API resolved / Integrated includes “Not required” only when a reason is recorded. Stages are counted independently.
Progress by release scope |  |  |  |  | Update routine
Release scope | Screens | Dev verified | Released |  | 1. Start with the MVP scope. Assess each screen, assign one accountable owner, sprint and due date.
MVP
Phase 2 |  |  |  |  | 2. Update stages, blockers, next action and last updated each day. Use the SCR ID in tasks and PRs.
Phase 3
3. QA records test evidence and open critical/high defects. The product owner records acceptance.
When development counts as verified
Frontend done, API and integration done or justified as not required, QA passed, acceptance accepted, zero open critical/high bugs and no blocker. |  |  |  |  | 4. Review blockers and overdue work daily. Review module delivery and the next sprint weekly.
5. Keep Shared Work current for services used by many screens. Record deployment after release.
Owner, work item / PR, QA evidence and last updated must also be recorded. A production deployment counts as released only when this gate passes.

## Screen Tracker
Screen development tracker
Amber cells are editable. Keep one row per SCR ID. Scroll right for evidence, calculated state and schedule.
Source: School_ERP_296_Mock_Screens_Source.zip, 296-screen registry. Mockup baseline: School_ERP_296_Bright_Screens.zip.
Screen ID | Screen name | Module | Release scope | Story IDs | Owner | Sprint | Due date | Mockup | Frontend | API / DB | Integration | QA | Acceptance | Open critical / high bugs | Deployment | Blocker / dependency | Next action | Work item / PR link | QA evidence link | Last updated | Not required reason | State (calculated) | Dev verified | Schedule (calculated) | Days overdue | Roles | Implemented at (audit)
SCR-001 | Landing / Home | Public Website & Authentication | MVP | US-0001, US-0002 |  |  |  | Ready | Done | Not required | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Hero, feature cards, portal links, health badge |  |  | 2026-09-20 | Hero, feature cards, portal links, health badge |  |  |  |  | All Users | /
SCR-002 | Workspace / Role Selection | Public Website & Authentication | MVP | US-0003, US-0004 |  |  |  | Ready | Done | Not required | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Every portal, with a line on picking the right one |  |  | 2026-09-20 | Every portal, with a line on picking the right one |  |  |  |  | All Users | /workspace
SCR-003 | Sign In | Public Website & Authentication | MVP | US-0005, US-0006 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Seven sign-in pages, each posts auth/login |  |  | 2026-09-20 | [5 empty] | All Users | /school/login and six other portals
SCR-004 | Forgot Password | Public Website & Authentication | MVP | US-0007, US-0008 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Same answer whether the account exists or not |  |  | 2026-09-20 | [5 empty] | All Users | /account/forgot-password
SCR-005 | Reset Password | Public Website & Authentication | MVP | US-0009, US-0010 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Code dies on use, on reissue and after five guesses |  |  | 2026-09-20 | [5 empty] | All Users | /account/reset-password
SCR-006 | OTP / Two-Factor Verification | Public Website & Authentication | Phase 2 | US-0011, US-0012 |  |  |  | Ready | Not started | Not started | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Parent login says OTP coming soon |  |  | 2026-09-20 | [5 empty] | All Users | -
SCR-007 | First Login / Change Password | Public Website & Authentication | Phase 2 | US-0013, US-0014 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Every guard forces it when somebody else set the password |  |  | 2026-09-20 | [5 empty] | All Users | /account/change-password
SCR-008 | Access Denied / Session Expired | Public Website & Authentication | Phase 2 | US-0015, US-0016 |  |  |  | Ready | Done | Not required | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Expired and forbidden, and the 401 interceptor routes here |  |  | 2026-09-20 | Expired and forbidden, and the 401 interceptor routes here |  |  |  |  | All Users | /account/denied
SCR-009 | Platform Dashboard | Super Admin / SaaS Administration | MVP | US-0017, US-0018 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Usage counters, renewals, CSV export |  |  | 2026-09-20 | [5 empty] | Super Admin | /super-admin
SCR-010 | Organizations List | Super Admin / SaaS Administration | MVP | US-0019, US-0020 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Paginated table with search and status |  |  | 2026-09-20 | [5 empty] | Super Admin | /super-admin/tenants
SCR-011 | Add Organization | Super Admin / SaaS Administration | MVP | US-0021, US-0022 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Creates tenant, school and admin |  |  | 2026-09-20 | [5 empty] | Super Admin | /super-admin/tenants
SCR-012 | Organization Details | Super Admin / SaaS Administration | Phase 2 | US-0023, US-0024 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Subscription, schools, usage, payments, suspend |  |  | 2026-09-20 | [5 empty] | Super Admin | /super-admin/tenants/[id]
SCR-013 | Subscription Plans | Super Admin / SaaS Administration | Phase 2 | US-0025, US-0026 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | List plus create and edit |  |  | 2026-09-20 | [5 empty] | Super Admin | /super-admin/plans
SCR-014 | Subscriptions & Billing | Super Admin / SaaS Administration | Phase 2 | US-0027, US-0028 |  |  |  | Ready | In progress | In progress | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Per-tenant cards, no billing screen |  |  | 2026-09-20 | [5 empty] | Super Admin | /super-admin/tenants/[id]
SCR-015 | Tenant Usage & Limits | Super Admin / SaaS Administration | Phase 2 | US-0029, US-0030 |  |  |  | Ready | In progress | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Usage versus quota card only |  |  | 2026-09-20 | [5 empty] | Super Admin | /super-admin/tenants/[id]
SCR-016 | Platform Users | Super Admin / SaaS Administration | Phase 3 | US-0031, US-0032 |  |  |  | Ready | Not started | Not started | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | No platform user management |  |  | 2026-09-20 | [5 empty] | Super Admin | -
SCR-017 | Support Tickets | Super Admin / SaaS Administration | Phase 3 | US-0033, US-0034 |  |  |  | Ready | Not started | Not started | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | No ticketing anywhere |  |  | 2026-09-20 | [5 empty] | Super Admin | -
SCR-018 | System Health & Service Status | Super Admin / SaaS Administration | Phase 3 | US-0035, US-0036 |  |  |  | Ready | In progress | In progress | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Online pill only, two health endpoints |  |  | 2026-09-20 | [5 empty] | Super Admin | /
SCR-019 | Global Announcements | Super Admin / SaaS Administration | Phase 3 | US-0037, US-0038 |  |  |  | Ready | Not started | Not started | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | No global announcements |  |  | 2026-09-20 | [5 empty] | Super Admin | -
SCR-020 | Platform Settings | Super Admin / SaaS Administration | Phase 3 | US-0039, US-0040 |  |  |  | Ready | Not started | Not started | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | No platform settings screen |  |  | 2026-09-20 | [5 empty] | Super Admin | -
SCR-021 | Organization Profile | Organization / School / Branch Setup | MVP | US-0041, US-0042 |  |  |  | Ready | In progress | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Read-only header; patch endpoint unused |  |  | 2026-09-20 | [5 empty] | Super Admin | /super-admin/tenants/[id]
SCR-022 | Schools List | Organization / School / Branch Setup | MVP | US-0043, US-0044 |  |  |  | Ready | In progress | In progress | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Name and code list only |  |  | 2026-09-20 | [5 empty] | Super Admin | /super-admin/tenants/[id]
SCR-023 | Add School | Organization / School / Branch Setup | MVP | US-0045, US-0046 |  |  |  | Ready | In progress | In progress | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | School only creatable with a new tenant |  |  | 2026-09-20 | [5 empty] | Super Admin | /super-admin/tenants
SCR-024 | School Details | Organization / School / Branch Setup | MVP | US-0047, US-0048 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Identity, contacts, address, timezone, currency |  |  | 2026-09-20 | [5 empty] | Super Admin | /school/profile
SCR-025 | Branches List | Organization / School / Branch Setup | MVP | US-0049, US-0050 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Branches table with head and counts |  |  | 2026-09-20 | [5 empty] | Super Admin | /school/roles
SCR-026 | Add Branch | Organization / School / Branch Setup | MVP | US-0051, US-0052 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Inline branch form with head and main flag |  |  | 2026-09-20 | [5 empty] | Super Admin | /school/roles
SCR-027 | Branch Details | Organization / School / Branch Setup | MVP | US-0053, US-0054 |  |  |  | Ready | In progress | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Edit form, no branch detail page |  |  | 2026-09-20 | [5 empty] | Super Admin | /school/roles
SCR-028 | Academic Year Setup | Organization / School / Branch Setup | MVP | US-0055, US-0056 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Create, set current, archive, terms |  |  | 2026-09-20 | [5 empty] | Super Admin | /school/academic-years
SCR-029 | Grade / Class Setup | Organization / School / Branch Setup | Phase 2 | US-0057, US-0058 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Create, rename, delete, reorder |  |  | 2026-09-20 | [5 empty] | Super Admin | /school/classes
SCR-030 | Section Setup | Organization / School / Branch Setup | Phase 2 | US-0059, US-0060 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Sections plus subject and teacher assignment |  |  | 2026-09-20 | [5 empty] | Super Admin | /school/classes
SCR-031 | Department Setup | Organization / School / Branch Setup | Phase 2 | US-0061, US-0062 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Create and update with head |  |  | 2026-09-20 | [5 empty] | Super Admin | /school/departments
SCR-032 | School Branding & Profile | Organization / School / Branch Setup | Phase 3 | US-0063, US-0064 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | App name, logo, brand colour |  |  | 2026-09-20 | [5 empty] | Super Admin | /school/profile
SCR-033 | School Admin Dashboard | Role Dashboards | MVP | US-0065, US-0066 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Dashboard stat cards and panels |  |  | 2026-09-20 | [5 empty] | School Admin | /school
SCR-034 | Principal Dashboard | Role Dashboards | MVP | US-0067, US-0068 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Principal overview dashboard |  |  | 2026-09-20 | [5 empty] | Principal | /principal
SCR-035 | Teacher Dashboard | Role Dashboards | MVP | US-0069, US-0070 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Today classes and stat cards |  |  | 2026-09-20 | [5 empty] | Teacher | /teacher
SCR-036 | Student Dashboard | Role Dashboards | MVP | US-0071, US-0072 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Homework due, today's lessons, attendance, notices |  |  | 2026-09-20 | [5 empty] | Student | /student
SCR-037 | Parent Dashboard | Role Dashboards | MVP | US-0073, US-0074 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Children cards, notices, holidays |  |  | 2026-09-20 | [5 empty] | Parent | /parent
SCR-038 | Accountant Dashboard | Role Dashboards | Phase 2 | US-0075, US-0076 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Collected today and this month against what is owed |  |  | 2026-09-20 | [5 empty] | Accountant | /accountant
SCR-039 | HR Dashboard | Role Dashboards | Phase 2 | US-0077, US-0078 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Staff and leave panel, shown to whoever holds hr.manage |  |  | 2026-09-20 | [5 empty] | HR | /staff
SCR-040 | Admission Officer Dashboard | Role Dashboards | Phase 3 | US-0079, US-0080 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Admissions panel, shown to whoever holds admissions.manage |  |  | 2026-09-20 | [5 empty] | Admission Officer | /staff
SCR-041 | Transport Manager Dashboard | Role Dashboards | Phase 3 | US-0081, US-0082 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Transport panel, shown to whoever holds transport.manage |  |  | 2026-09-20 | [5 empty] | Transport Manager | /staff
SCR-042 | Librarian Dashboard | Role Dashboards | Phase 3 | US-0083, US-0084 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Library panel, shown to whoever holds library.manage |  |  | 2026-09-20 | [5 empty] | Librarian | /staff
SCR-043 | Admission / Enquiry Dashboard | Admissions & Enquiries | MVP | US-0085, US-0086 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Funnel, plus what is waiting on us |  |  | 2026-09-20 | [5 empty] | Admission Officer | /school/admissions/dashboard
SCR-044 | Enquiry List | Admissions & Enquiries | MVP | US-0087, US-0088 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Stage, source and follow-up filters with paging |  |  | 2026-09-20 | [5 empty] | Admission Officer | /school/admissions
SCR-045 | Add Enquiry | Admissions & Enquiries | MVP | US-0089, US-0090 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | New enquiry modal, full field set |  |  | 2026-09-20 | [5 empty] | Admission Officer | /school/admissions
SCR-046 | Enquiry Details | Admissions & Enquiries | MVP | US-0091, US-0092 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Stage moves, timeline, convert, lost |  |  | 2026-09-20 | [5 empty] | Admission Officer | /school/admissions/[id]
SCR-047 | Follow-up Calendar | Admissions & Enquiries | MVP | US-0093, US-0094 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Grouped overdue, today, this week, later |  |  | 2026-09-20 | [5 empty] | Admission Officer | /school/admissions/follow-ups
SCR-048 | Admission Applications | Admissions & Enquiries | MVP | US-0095, US-0096 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Status filter, search, list |  |  | 2026-09-20 | [5 empty] | Admission Officer | /school/admissions/applications
SCR-049 | New Admission Application | Admissions & Enquiries | MVP | US-0097, US-0098 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Staff modal and public form both exist |  |  | 2026-09-20 | [5 empty] | Admission Officer | /apply/[tenant]/[school]/application
SCR-050 | Application Details | Admissions & Enquiries | Phase 2 | US-0099, US-0100 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Profile, docs, assessments, fee, history |  |  | 2026-09-20 | [5 empty] | Admission Officer | /school/admissions/applications
SCR-051 | Document Verification | Admissions & Enquiries | Phase 2 | US-0101, US-0102 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | One queue across applications, verify or reject with a reason |  |  | 2026-09-20 | [5 empty] | Admission Officer | /school/admissions/verification
SCR-052 | Entrance Assessment | Admissions & Enquiries | Phase 2 | US-0103, US-0104 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | A form, not a prompt; scheduled kept apart from marked |  |  | 2026-09-20 | [5 empty] | Admission Officer | /school/admissions/assessments
SCR-053 | Admission Approval | Admissions & Enquiries | Phase 3 | US-0105, US-0106 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Approve and reject in a modal with the evidence on screen |  |  | 2026-09-20 | [5 empty] | Admission Officer | /school/admissions/decisions
SCR-054 | Admission Confirmation & Student Creation | Admissions & Enquiries | Phase 3 | US-0107, US-0108 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Creates student and parent login with password |  |  | 2026-09-20 | [5 empty] | Admission Officer | /school/admissions/applications
SCR-055 | Student Directory | Students | MVP | US-0109, US-0110 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Year, class, section, status filters and search |  |  | 2026-09-20 | [5 empty] | School Admin | /school/students
SCR-056 | Add Student | Students | MVP | US-0111, US-0112 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Admit modal plus bulk CSV import |  |  | 2026-09-20 | [5 empty] | School Admin | /school/students
SCR-057 | Student Profile Overview | Students | MVP | US-0113, US-0114 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Stats, attendance, exams, behaviour, homework |  |  | 2026-09-20 | [5 empty] | School Admin | /school/students/[id]
SCR-058 | Edit Student | Students | MVP | US-0115, US-0116 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Edit name, section, roll, DOB, blood, address |  |  | 2026-09-20 | [5 empty] | School Admin | /school/students
SCR-059 | Student Academic Details | Students | MVP | US-0117, US-0118 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Subjects with teachers, and the years behind |  |  | 2026-09-20 | [5 empty] | School Admin | /school/students/[id]/academic
SCR-060 | Student Attendance History | Students | MVP | US-0119, US-0120 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Attendance tab: months, percent and days away |  |  | 2026-09-20 | [5 empty] | School Admin | /school/students/[id]
SCR-061 | Student Examination & Results | Students | MVP | US-0121, US-0122 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Per paper, with unmarked kept apart from nought |  |  | 2026-09-20 | [5 empty] | School Admin | /school/students/[id]/exams
SCR-062 | Student Fees & Ledger | Students | MVP | US-0123, US-0124 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Fees tab scoped to the child |  |  | 2026-09-20 | [5 empty] | School Admin | /school/students/[id]
SCR-063 | Student Documents | Students | Phase 2 | US-0125, US-0126 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Documents tab with download |  |  | 2026-09-20 | [5 empty] | School Admin | /school/students/[id]
SCR-064 | Student Behaviour & Discipline | Students | Phase 2 | US-0127, US-0128 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Conduct tab: incidents for this child |  |  | 2026-09-20 | [5 empty] | School Admin | /school/students/[id]
SCR-065 | Student Health | Students | Phase 2 | US-0129, US-0130 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Full per-student health record |  |  | 2026-09-20 | [5 empty] | School Admin | /school/health/students/[id]
SCR-066 | Student Transport | Students | Phase 3 | US-0131, US-0132 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Search by student, assign, move, end |  |  | 2026-09-20 | [5 empty] | School Admin | /school/transport/students
SCR-067 | Student Library | Students | Phase 3 | US-0133, US-0134 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Library tab: loans, overdue and fines |  |  | 2026-09-20 | [5 empty] | School Admin | /school/students/[id]
SCR-068 | Siblings & Family | Students | Phase 3 | US-0135, US-0136 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Siblings derived from shared parents, never stored |  |  | 2026-09-20 | [5 empty] | School Admin | /school/students/[id]/family
SCR-069 | Promotion / Transfer | Students | Phase 3 | US-0137, US-0138 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Bulk promote plus section change |  |  | 2026-09-20 | [5 empty] | School Admin | /school/students
SCR-070 | Student Exit / Alumni Conversion | Students | Phase 3 | US-0139, US-0140 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Derived from enrolment; flags leavers with no certificate |  |  | 2026-09-20 | [5 empty] | School Admin | /school/students/leavers
SCR-071 | Parent / Guardian Directory | Parents & Guardians | MVP | US-0141, US-0142 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Search, status filter, linked children |  |  | 2026-09-20 | [5 empty] | School Admin | /school/parents
SCR-072 | Add Parent / Guardian | Parents & Guardians | MVP | US-0143, US-0144 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Creates login, links a child, temp password |  |  | 2026-09-20 | [5 empty] | School Admin | /school/parents
SCR-073 | Parent Profile | Parents & Guardians | MVP | US-0145, US-0146 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Profile, linked children, activate and reset |  |  | 2026-09-20 | [5 empty] | School Admin | /school/parents/[id]
SCR-074 | Link Children | Parents & Guardians | MVP | US-0147, US-0148 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Link and unlink children with relation |  |  | 2026-09-20 | [5 empty] | School Admin | /school/parents
SCR-075 | Communication Preferences | Parents & Guardians | Phase 2 | US-0149, US-0150 |  |  |  | Ready | Not started | Not started | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | No notification preference UI or model |  |  | 2026-09-20 | [5 empty] | School Admin | -
SCR-076 | Parent Login Access | Parents & Guardians | Phase 2 | US-0151, US-0152 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Activate, deactivate, reset password |  |  | 2026-09-20 | [5 empty] | School Admin | /school/parents
SCR-077 | Parent-Teacher Interactions | Parents & Guardians | Phase 3 | US-0153, US-0154 |  |  |  | Ready | In progress | In progress | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Meetings and slots; messages are teacher-only |  |  | 2026-09-20 | [5 empty] | School Admin | /school/ptm
SCR-078 | Parent Payments & Receipts | Parents & Guardians | Phase 3 | US-0155, US-0156 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Across all their children, not one at a time |  |  | 2026-09-20 | [5 empty] | School Admin | /school/parents/[id]/payments
SCR-079 | Parent Activity History | Parents & Guardians | Phase 3 | US-0157, US-0158 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Audit by actor and by subject, sign-ins stated as unrecorded |  |  | 2026-09-20 | [5 empty] | School Admin | /school/parents/[id]/activity
SCR-080 | Staff Directory | Teachers & Staff | MVP | US-0159, US-0160 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Role and status filters with search |  |  | 2026-09-20 | [5 empty] | School Admin | /school/staff
SCR-081 | Add Staff | Teachers & Staff | MVP | US-0161, US-0162 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Creates staff and login with temp password |  |  | 2026-09-20 | [5 empty] | School Admin | /school/staff
SCR-082 | Staff Profile | Teachers & Staff | MVP | US-0163, US-0164 |  |  |  | Ready | In progress | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | No staff profile page, only a row and modal |  |  | 2026-09-20 | [5 empty] | School Admin | /school/staff
SCR-083 | Edit Staff | Teachers & Staff | MVP | US-0165, US-0166 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Name, phone, number, designation, department |  |  | 2026-09-20 | [5 empty] | School Admin | /school/staff
SCR-084 | Teacher Allocation | Teachers & Staff | MVP | US-0167, US-0168 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Class teacher plus subject teacher per class |  |  | 2026-09-20 | [5 empty] | School Admin | /school/classes
SCR-085 | Subject & Class Assignment | Teachers & Staff | MVP | US-0169, US-0170 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Assign subjects and teacher per class-subject |  |  | 2026-09-20 | [5 empty] | School Admin | /school/classes
SCR-086 | Teacher Workload | Teachers & Staff | Phase 2 | US-0171, US-0172 |  |  |  | Ready | Not started | In progress | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | No workload view anywhere |  |  | 2026-09-20 | [5 empty] | School Admin | -
SCR-087 | Qualifications & Documents | Teachers & Staff | Phase 2 | US-0173, US-0174 |  |  |  | Ready | In progress | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | No qualification fields on the staff record |  |  | 2026-09-20 | [5 empty] | School Admin | /school/documents
SCR-088 | Staff Attendance Summary | Teachers & Staff | Phase 3 | US-0175, US-0176 |  |  |  | Ready | In progress | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Single day only; no monthly summary |  |  | 2026-09-20 | [5 empty] | School Admin | /school/staff-attendance
SCR-089 | Staff Leave Summary | Teachers & Staff | Phase 3 | US-0177, US-0178 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Decisions plus per-employee balances |  |  | 2026-09-20 | [5 empty] | School Admin | /school/staff-leaves
SCR-090 | Performance & Classroom Observation | Teachers & Staff | Phase 3 | US-0179, US-0180 |  |  |  | Ready | Not started | Not started | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | No observation or appraisal anywhere |  |  | 2026-09-20 | [5 empty] | School Admin | -
SCR-091 | Exit / Offboarding | Teachers & Staff | Phase 3 | US-0181, US-0182 |  |  |  | Ready | In progress | In progress | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Deactivate only; no clearance or exit flow |  |  | 2026-09-20 | [5 empty] | School Admin | /school/staff
SCR-092 | Academic Years | Academics & Curriculum | MVP | US-0183, US-0184 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Full CRUD, archive, set-current |  |  | 2026-09-20 | [5 empty] | Academic Coordinator | /school/academic-years
SCR-093 | Terms / Semesters | Academics & Curriculum | MVP | US-0185, US-0186 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Terms per year with overlap guard |  |  | 2026-09-20 | [5 empty] | Academic Coordinator | /school/terms
SCR-094 | Grades / Classes | Academics & Curriculum | MVP | US-0187, US-0188 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Create, rename, reorder, delete classes |  |  | 2026-09-20 | [5 empty] | Academic Coordinator | /school/classes
SCR-095 | Sections | Academics & Curriculum | MVP | US-0189, US-0190 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Sections are a nested list inside Classes (in a tab, complete) |  |  | 2026-09-20 | [5 empty] | Academic Coordinator | /school/classes
SCR-096 | Subjects | Academics & Curriculum | MVP | US-0191, US-0192 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | CRUD, code, kind, department, bulk paste |  |  | 2026-09-20 | [5 empty] | Academic Coordinator | /school/subjects
SCR-097 | Subject Groups | Academics & Curriculum | MVP | US-0193, US-0194 |  |  |  | Ready | Not started | Not started | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | No subject-group entity anywhere |  |  | 2026-09-20 | [5 empty] | Academic Coordinator | -
SCR-098 | Curriculum | Academics & Curriculum | MVP | US-0195, US-0196 |  |  |  | Ready | In progress | In progress | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | No curriculum entity with board and status |  |  | 2026-09-20 | [5 empty] | Academic Coordinator | /school/syllabus
SCR-099 | Curriculum Details | Academics & Curriculum | MVP | US-0197, US-0198 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Chapters, topics, progress, copy |  |  | 2026-09-20 | [5 empty] | Academic Coordinator | /school/syllabus/[id]
SCR-100 | Units / Chapters / Topics | Academics & Curriculum | MVP | US-0199, US-0200 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Chapter and topic tree, reorder, periods |  |  | 2026-09-20 | [5 empty] | Academic Coordinator | /school/syllabus/[id]
SCR-101 | Learning Outcomes | Academics & Curriculum | Phase 2 | US-0201, US-0202 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Outcomes tab with coverage (in a tab, complete) |  |  | 2026-09-20 | [5 empty] | Academic Coordinator | /school/syllabus/[id]/curriculum
SCR-102 | Lesson Plans | Academics & Curriculum | Phase 2 | US-0203, US-0204 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | List with status filter |  |  | 2026-09-20 | [5 empty] | Academic Coordinator | /teacher/lesson-plans
SCR-103 | Create / Edit Lesson Plan | Academics & Curriculum | Phase 2 | US-0205, US-0206 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Create and edit plan modal |  |  | 2026-09-20 | [5 empty] | Academic Coordinator | /teacher/lesson-plans
SCR-104 | Lesson Plan Review & Approval | Academics & Curriculum | Phase 2 | US-0207, US-0208 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Reviewer mode, approve or return |  |  | 2026-09-20 | [5 empty] | Academic Coordinator | /principal/lesson-plans
SCR-105 | Syllabus Progress | Academics & Curriculum | Phase 3 | US-0209, US-0210 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Per-section progress and behind-plan count |  |  | 2026-09-20 | [5 empty] | Academic Coordinator | /school/syllabus
SCR-106 | Teaching Resources | Academics & Curriculum | Phase 3 | US-0211, US-0212 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Resources tab, file or link (in a tab, complete) |  |  | 2026-09-20 | [5 empty] | Academic Coordinator | /school/syllabus/[id]/curriculum
SCR-107 | Classroom / Room Management | Academics & Curriculum | Phase 3 | US-0213, US-0214 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Rooms with building, floor, kind, capacity |  |  | 2026-09-20 | [5 empty] | Academic Coordinator | /school/facilities
SCR-108 | Academic Calendar | Academics & Curriculum | Phase 3 | US-0215, US-0216 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Events, holidays, exams and PTM in one feed |  |  | 2026-09-20 | [5 empty] | Academic Coordinator | /school/calendar
SCR-109 | Co-Curricular Activities | Academics & Curriculum | Phase 3 | US-0217, US-0218 |  |  |  | Ready | Not started | Not started | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | No activity or club register |  |  | 2026-09-20 | [5 empty] | Academic Coordinator | -
SCR-110 | Daily Class Attendance | Student Attendance | MVP | US-0219, US-0220 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Roster, statuses, bulk set, edit window |  |  | 2026-09-20 | [5 empty] | Teacher | /teacher/attendance
SCR-111 | Period / Subject Attendance | Student Attendance | MVP | US-0221, US-0222 |  |  |  | Ready | Not started | Not started | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Attendance keyed by section and date only |  |  | 2026-09-20 | [5 empty] | Teacher | -
SCR-112 | Student Attendance Register | Student Attendance | MVP | US-0223, US-0224 |  |  |  | Ready | In progress | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Matrix is an admin tab; teachers have none |  |  | 2026-09-20 | [5 empty] | Teacher | /school/reports/attendance
SCR-113 | Attendance Correction | Student Attendance | MVP | US-0225, US-0226 |  |  |  | Ready | In progress | In progress | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Reopen only; no per-student correction request |  |  | 2026-09-20 | [5 empty] | Class Teacher | /school/attendance-registers
SCR-114 | Student Leave Requests | Student Attendance | MVP | US-0227, US-0228 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Apply and history, parent-initiated |  |  | 2026-09-20 | [5 empty] | Teacher | /parent/children/[id]/leave
SCR-115 | Student Leave Approval | Student Attendance | Phase 2 | US-0229, US-0230 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Approve or reject with note |  |  | 2026-09-20 | [5 empty] | Class Teacher | /school/student-leaves
SCR-116 | Late Entry / Early Exit | Student Attendance | Phase 2 | US-0231, US-0232 |  |  |  | Ready | In progress | In progress | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Gate passes cover exit, not late entry |  |  | 2026-09-20 | [5 empty] | Teacher | /school/front-desk
SCR-117 | Monthly Attendance Summary | Student Attendance | Phase 2 | US-0233, US-0234 |  |  |  | Ready | In progress | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | One tab of three, with CSV |  |  | 2026-09-20 | [5 empty] | School Admin | /school/reports/attendance
SCR-118 | Chronic Absence Alerts | Student Attendance | Phase 3 | US-0235, US-0236 |  |  |  | Ready | Not started | Not started | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | No threshold, at-risk list or contact log |  |  | 2026-09-20 | [5 empty] | School Admin | -
SCR-119 | Attendance Reports | Student Attendance | Phase 3 | US-0237, US-0238 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Daily, class and student views with CSV |  |  | 2026-09-20 | [5 empty] | School Admin | /school/reports/attendance
SCR-120 | Timetable Dashboard | Timetable & Substitution | MVP | US-0239, US-0240 |  |  |  | Ready | In progress | In progress | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Only a clashes panel, no dashboard stats |  |  | 2026-09-20 | [5 empty] | Academic Coordinator | /school/timetable
SCR-121 | Timetable Setup | Timetable & Substitution | MVP | US-0241, US-0242 |  |  |  | Ready | In progress | In progress | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Grid assigns subject; entries carry no room |  |  | 2026-09-20 | [5 empty] | Academic Coordinator | /school/timetable
SCR-122 | Period Setup | Timetable & Substitution | MVP | US-0243, US-0244 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Per-day periods with times |  |  | 2026-09-20 | [5 empty] | Academic Coordinator | /school/periods
SCR-123 | Teacher Availability | Timetable & Substitution | MVP | US-0245, US-0246 |  |  |  | Ready | In progress | In progress | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Date-range blocks, not a weekly grid |  |  | 2026-09-20 | [5 empty] | Academic Coordinator | /school/cover
SCR-124 | Generate Timetable | Timetable & Substitution | Phase 2 | US-0247, US-0248 |  |  |  | Ready | Not started | Not started | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | No generator; manual entry and copy only |  |  | 2026-09-20 | [5 empty] | Academic Coordinator | -
SCR-125 | Class Timetable | Timetable & Substitution | Phase 2 | US-0249, US-0250 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Section grid with publish; parent read-only |  |  | 2026-09-20 | [5 empty] | Academic Coordinator | /school/timetable
SCR-126 | Teacher Timetable | Timetable & Substitution | Phase 2 | US-0251, US-0252 |  |  |  | Ready | In progress | In progress | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Own week only; no coordinator view |  |  | 2026-09-20 | [5 empty] | Academic Coordinator | /teacher/timetable
SCR-127 | Substitution / Replacement | Timetable & Substitution | Phase 3 | US-0253, US-0254 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Uncovered slots, candidates, assign, auto-assign |  |  | 2026-09-20 | [5 empty] | Academic Coordinator | /school/cover
SCR-128 | Homework List | Homework & Assignments | MVP | US-0255, US-0256 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | List with due dates, counts, close and reopen |  |  | 2026-09-20 | [5 empty] | Teacher | /teacher/homework
SCR-129 | Create Homework | Homework & Assignments | MVP | US-0257, US-0258 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Create modal with rubric and attachment |  |  | 2026-09-20 | [5 empty] | Teacher | /teacher/homework
SCR-130 | Homework Details | Homework & Assignments | MVP | US-0259, US-0260 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Submissions in a modal, no detail page (in a tab, complete) |  |  | 2026-09-20 | [5 empty] | Teacher | /teacher/homework
SCR-131 | Student Homework View | Homework & Assignments | MVP | US-0261, US-0262 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | The child sees their own homework, not via a parent |  |  | 2026-09-20 | [5 empty] | Student | /student/homework
SCR-132 | Homework Submission | Homework & Assignments | MVP | US-0263, US-0264 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | The child hands work in themselves; the record says who did |  |  | 2026-09-20 | [5 empty] | Student | /student/homework
SCR-133 | Homework Evaluation | Homework & Assignments | MVP | US-0265, US-0266 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Approve, reject and rubric marks in a modal (in a tab, complete) |  |  | 2026-09-20 | [5 empty] | Teacher | /teacher/homework
SCR-134 | Assignment List | Homework & Assignments | Phase 2 | US-0267, US-0268 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Project list with progress counts |  |  | 2026-09-20 | [5 empty] | Teacher | /teacher/projects
SCR-135 | Create Assignment | Homework & Assignments | Phase 2 | US-0269, US-0270 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Create modal with dates and attachment |  |  | 2026-09-20 | [5 empty] | Teacher | /teacher/projects
SCR-136 | Assignment Submissions | Homework & Assignments | Phase 2 | US-0271, US-0272 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Submission with teacher remark and review state |  |  | 2026-09-20 | [5 empty] | Student | /student/homework
SCR-137 | Assignment Evaluation | Homework & Assignments | Phase 3 | US-0273, US-0274 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Per-student remark and rating in a modal (in a tab, complete) |  |  | 2026-09-20 | [5 empty] | Teacher | /teacher/projects
SCR-138 | Exam Dashboard | Examinations / Marks / Results | MVP | US-0275, US-0276 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Readiness checklist per paper, with what blocks publication |  |  | 2026-09-20 | [5 empty] | Exam Coordinator | /school/exams/[id]
SCR-139 | Exam Types | Examinations / Marks / Results | MVP | US-0277, US-0278 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Exam types are one card among three (in a tab, complete) |  |  | 2026-09-20 | [5 empty] | Exam Coordinator | /school/grading
SCR-140 | Exam Setup | Examinations / Marks / Results | MVP | US-0279, US-0280 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Create exam and add papers with marks |  |  | 2026-09-20 | [5 empty] | Exam Coordinator | /school/exams
SCR-141 | Exam Schedule | Examinations / Marks / Results | MVP | US-0281, US-0282 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Papers by day, with per-class clash detection |  |  | 2026-09-20 | [5 empty] | Exam Coordinator | /school/exams/[id]/datesheet
SCR-142 | Hall / Room Allocation | Examinations / Marks / Results | MVP | US-0283, US-0284 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Room allocation, fills in order, move a child |  |  | 2026-09-20 | [5 empty] | Exam Coordinator | /school/exams/[id]/halls
SCR-143 | Invigilation Assignment | Examinations / Marks / Results | MVP | US-0285, US-0286 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Per-room duty with double-booking refused, plus roster |  |  | 2026-09-20 | [5 empty] | Exam Coordinator | /school/exams/[id]/invigilation
SCR-144 | Admit Card | Examinations / Marks / Results | MVP | US-0287, US-0288 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Per class, with room per paper, prints as PDF |  |  | 2026-09-20 | [5 empty] | Exam Coordinator | /school/exams/[id]/admit-cards
SCR-145 | Marks Entry | Examinations / Marks / Results | MVP | US-0289, US-0290 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Roster, status, marks, live grade, save |  |  | 2026-09-20 | [5 empty] | Teacher | /teacher/marks/papers/[id]
SCR-146 | Practical / Internal Marks | Examinations / Marks / Results | Phase 2 | US-0291, US-0292 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Parts must add up; the total is their sum |  |  | 2026-09-20 | [5 empty] | Teacher | /school/exams/papers/[paperId]/components
SCR-147 | Bulk Marks Import | Examinations / Marks / Results | Phase 2 | US-0293, US-0294 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Teacher uploads for their own paper, checked before written |  |  | 2026-09-20 | [5 empty] | Teacher | /teacher/marks/papers/[id]/import
SCR-148 | Marks Verification | Examinations / Marks / Results | Phase 2 | US-0295, US-0296 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Sign off a paper; refuses whoever entered the marks |  |  | 2026-09-20 | [5 empty] | Teacher | /school/exams
SCR-149 | Grade / Grading Setup | Examinations / Marks / Results | Phase 2 | US-0297, US-0298 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Scale CRUD, bands, seed, default |  |  | 2026-09-20 | [5 empty] | Exam Coordinator | /school/grading
SCR-150 | Publish Results | Examinations / Marks / Results | Phase 3 | US-0299, US-0300 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Principal publishes, told what is outstanding first |  |  | 2026-09-20 | [5 empty] | Principal | /principal/exams
SCR-151 | Student Result | Examinations / Marks / Results | Phase 3 | US-0301, US-0302 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Published only, withheld stays withheld |  |  | 2026-09-20 | [5 empty] | Student | /student/exams/[examId]
SCR-152 | Report Card | Examinations / Marks / Results | Phase 3 | US-0303, US-0304 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Same renderer as the school and the parents |  |  | 2026-09-20 | [5 empty] | Student | /student/exams/[examId]
SCR-153 | Promotion Decision | Examinations / Marks / Results | Phase 3 | US-0305, US-0306 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Result-driven suggestion, review kept apart from fail |  |  | 2026-09-20 | [5 empty] | Principal | /school/exams/[id]/promotion
SCR-154 | Fee Dashboard | Fees & Finance | MVP | US-0307, US-0308 |  |  |  | Ready | In progress | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Accountant dashboard is a placeholder |  |  | 2026-09-20 | [5 empty] | Accountant | /accountant
SCR-155 | Fee Structure | Fees & Finance | MVP | US-0309, US-0310 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Per class, head and year |  |  | 2026-09-20 | [5 empty] | Accountant | /school/fees/structures
SCR-156 | Create / Edit Fee Structure | Fees & Finance | MVP | US-0311, US-0312 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Amount, due day, recurring flag |  |  | 2026-09-20 | [5 empty] | Accountant | /school/fees/structures
SCR-157 | Student Fee Assignment | Fees & Finance | MVP | US-0313, US-0314 |  |  |  | Ready | Not started | Not started | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | No per-student fee plan; class structures only |  |  | 2026-09-20 | [5 empty] | Accountant | -
SCR-158 | Fee Collection | Fees & Finance | MVP | US-0315, US-0316 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Record payment with mode and reference |  |  | 2026-09-20 | [5 empty] | Accountant | /school/fees
SCR-159 | Online Payment | Fees & Finance | MVP | US-0317, US-0318 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Razorpay checkout, verify, failures |  |  | 2026-09-20 | [5 empty] | Parent | /parent/children/[id]/fees
SCR-160 | Payment Receipt | Fees & Finance | MVP | US-0319, US-0320 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Per-order receipt PDF |  |  | 2026-09-20 | [5 empty] | Parent | /parent/children/[id]/fees
SCR-161 | Student Ledger | Fees & Finance | MVP | US-0321, US-0322 |  |  |  | Ready | In progress | In progress | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | No staff-side per-student ledger |  |  | 2026-09-20 | [5 empty] | Accountant | /parent/children/[id]/fees
SCR-162 | Outstanding Dues | Fees & Finance | Phase 2 | US-0323, US-0324 |  |  |  | Ready | In progress | In progress | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | A filter, not a dues or ageing report |  |  | 2026-09-20 | [5 empty] | Accountant | /school/fees
SCR-163 | Concession / Scholarship | Fees & Finance | Phase 2 | US-0325, US-0326 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Concessions: add, amend, end |  |  | 2026-09-20 | [5 empty] | Accountant | /school/accounts
SCR-164 | Fine Rules | Fees & Finance | Phase 2 | US-0327, US-0328 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Rule CRUD with preview and charge |  |  | 2026-09-20 | [5 empty] | Accountant | /school/fees/late-refunds
SCR-165 | Refunds | Fees & Finance | Phase 2 | US-0329, US-0330 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Request, decide, pay out with reference |  |  | 2026-09-20 | [5 empty] | Accountant | /school/fees/late-refunds
SCR-166 | Income | Fees & Finance | Phase 3 | US-0331, US-0332 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Other income with source, mode, void |  |  | 2026-09-20 | [5 empty] | Accountant | /school/accounts
SCR-167 | Expenses | Fees & Finance | Phase 3 | US-0333, US-0334 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Expenses with void and reason |  |  | 2026-09-20 | [5 empty] | Accountant | /school/accounts
SCR-168 | Vendor Management | Fees & Finance | Phase 3 | US-0335, US-0336 |  |  |  | Ready | In progress | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Supplier master; no ledger or payables |  |  | 2026-09-20 | [5 empty] | Accountant | /school/inventory
SCR-169 | Purchase / Payment | Fees & Finance | Phase 3 | US-0337, US-0338 |  |  |  | Ready | In progress | In progress | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | No purchase order, bill or payment tracking |  |  | 2026-09-20 | [5 empty] | Accountant | /school/inventory
SCR-170 | Cash & Bank Book | Fees & Finance | Phase 3 | US-0339, US-0340 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Cash book by mode across a date range |  |  | 2026-09-20 | [5 empty] | Accountant | /school/accounts
SCR-171 | Finance Reports | Fees & Finance | Phase 3 | US-0341, US-0342 |  |  |  | Ready | In progress | In progress | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | CSV and builder; no finance report pack |  |  | 2026-09-20 | [5 empty] | Accountant | /school/exports
SCR-172 | Recruitment Requisitions | HR / Leave / Payroll | Phase 2 | US-0343, US-0344 |  |  |  | Ready | Not started | Not started | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | No requisition or approval to hire |  |  | 2026-09-20 | [5 empty] | HR | -
SCR-173 | Job Openings | HR / Leave / Payroll | Phase 2 | US-0345, US-0346 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Create, publish, close, careers flag |  |  | 2026-09-20 | [5 empty] | HR | /school/recruitment
SCR-174 | Candidate Applications | HR / Leave / Payroll | Phase 2 | US-0347, US-0348 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Opening and stage filters with moves |  |  | 2026-09-20 | [5 empty] | HR | /school/recruitment
SCR-175 | Candidate Details | HR / Leave / Payroll | Phase 2 | US-0349, US-0350 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Candidate detail in a modal only (in a tab, complete) |  |  | 2026-09-20 | [5 empty] | HR | /school/recruitment
SCR-176 | Interview Schedule | HR / Leave / Payroll | Phase 2 | US-0351, US-0352 |  |  |  | Ready | In progress | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Per application; no interview calendar |  |  | 2026-09-20 | [5 empty] | HR | /school/recruitment
SCR-177 | Offer & Appointment | HR / Leave / Payroll | Phase 2 | US-0353, US-0354 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Draft, send, respond, hire creates staff |  |  | 2026-09-20 | [5 empty] | HR | /school/recruitment
SCR-178 | Employee Onboarding Checklist | HR / Leave / Payroll | Phase 2 | US-0355, US-0356 |  |  |  | Ready | Not started | Not started | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | No onboarding checklist anywhere |  |  | 2026-09-20 | [5 empty] | HR | -
SCR-179 | Staff Attendance Management | HR / Leave / Payroll | Phase 3 | US-0357, US-0358 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Check in and out with override |  |  | 2026-09-20 | [5 empty] | HR | /school/staff-attendance
SCR-180 | Leave Policies | HR / Leave / Payroll | Phase 3 | US-0359, US-0360 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Days, carry forward, paid, proof |  |  | 2026-09-20 | [5 empty] | HR | /school/leave-entitlement
SCR-181 | Staff Leave Requests | HR / Leave / Payroll | Phase 3 | US-0361, US-0362 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Pending and history across staff |  |  | 2026-09-20 | [5 empty] | HR | /school/staff-leaves
SCR-182 | Leave Approval | HR / Leave / Payroll | Phase 3 | US-0363, US-0364 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Decide on the list; no approver queue (in a tab, complete) |  |  | 2026-09-20 | [5 empty] | HR | /school/staff-leaves
SCR-183 | Payroll Setup | HR / Leave / Payroll | Phase 3 | US-0365, US-0366 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Salary structure plus statutory rates |  |  | 2026-09-20 | [5 empty] | HR | /school/payroll
SCR-184 | Payroll Processing | HR / Leave / Payroll | Phase 3 | US-0367, US-0368 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Recalculate, finalise, adjust, bank file |  |  | 2026-09-20 | [5 empty] | HR | /school/payroll/runs/[id]
SCR-185 | Payslip & Payroll History | HR / Leave / Payroll | Phase 3 | US-0369, US-0370 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Payslip PDF and month history |  |  | 2026-09-20 | [5 empty] | HR | /school/payroll
SCR-186 | Vehicles | Transport / Bus / GPS | Phase 2 | US-0371, US-0372 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Fleet table with document expiry and CRUD |  |  | 2026-09-20 | [5 empty] | Transport Manager | /school/transport/vehicles
SCR-187 | Add / Edit Vehicle | Transport / Bus / GPS | Phase 2 | US-0373, US-0374 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Create and edit with four document expiries |  |  | 2026-09-20 | [5 empty] | Transport Manager | /school/transport/vehicles
SCR-188 | Vehicle Details | Transport / Bus / GPS | Phase 2 | US-0375, US-0376 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Expiries flagged, fuel and service log |  |  | 2026-09-20 | [5 empty] | Transport Manager | /school/transport/vehicles/[id]
SCR-189 | Routes | Transport / Bus / GPS | Phase 2 | US-0377, US-0378 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Route cards with stop table |  |  | 2026-09-20 | [5 empty] | Transport Manager | /school/transport/routes
SCR-190 | Create / Edit Route | Transport / Bus / GPS | Phase 2 | US-0379, US-0380 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Route editor with reorderable stops |  |  | 2026-09-20 | [5 empty] | Transport Manager | /school/transport/routes
SCR-191 | Stops | Transport / Bus / GPS | Phase 2 | US-0381, US-0382 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Stops in order with times, and the riders |  |  | 2026-09-20 | [5 empty] | Transport Manager | /school/transport/routes/[id]
SCR-192 | Drivers & Conductors | Transport / Bus / GPS | Phase 3 | US-0383, US-0384 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Drivers and conductors with licence expiry |  |  | 2026-09-20 | [5 empty] | Transport Manager | /school/transport/crew
SCR-193 | Student Route Assignment | Transport / Bus / GPS | Phase 3 | US-0385, US-0386 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Assign, move, end with route and stop |  |  | 2026-09-20 | [5 empty] | Transport Manager | /school/transport/students
SCR-194 | Trip Sheet | Transport / Bus / GPS | Phase 3 | US-0387, US-0388 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Generate sheets, start, complete, odometer |  |  | 2026-09-20 | [5 empty] | Transport Manager | /school/transport/trips/[id]
SCR-195 | Live GPS Tracking | Transport / Bus / GPS | Phase 3 | US-0389, US-0390 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Last reported position, staleness stated |  |  | 2026-09-20 | [5 empty] | Transport Manager | /school/transport/live
SCR-196 | Boarding / Drop Attendance | Transport / Bus / GPS | Phase 3 | US-0391, US-0392 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Per-student boarded, dropped, absent |  |  | 2026-09-20 | [5 empty] | Transport Manager | /school/transport/trips/[id]
SCR-197 | Vehicle Maintenance & Fuel | Transport / Bus / GPS | Phase 3 | US-0393, US-0394 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Fuel and service entries with odometer |  |  | 2026-09-20 | [5 empty] | Transport Manager | /school/transport/vehicles/[id]
SCR-198 | Library Catalogue | Library | Phase 2 | US-0395, US-0396 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Search with category and shelf filters |  |  | 2026-09-20 | [5 empty] | Librarian | /school/library/catalogue
SCR-199 | Add / Edit Book | Library | Phase 2 | US-0397, US-0398 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Book form with initial copies and price |  |  | 2026-09-20 | [5 empty] | Librarian | /school/library/catalogue
SCR-200 | Book Details & Copies | Library | Phase 2 | US-0399, US-0400 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Copies table, statuses, add copies |  |  | 2026-09-20 | [5 empty] | Librarian | /school/library/catalogue/[id]
SCR-201 | Library Members | Library | Phase 2 | US-0401, US-0402 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Who holds what, with limit and can-borrow |  |  | 2026-09-20 | [5 empty] | Librarian | /school/library/members
SCR-202 | Issue Book | Library | Phase 2 | US-0403, US-0404 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Borrower and accession scan with due date |  |  | 2026-09-20 | [5 empty] | Librarian | /school/library
SCR-203 | Return Book | Library | Phase 3 | US-0405, US-0406 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Return with damage flag and fine |  |  | 2026-09-20 | [5 empty] | Librarian | /school/library
SCR-204 | Renew / Reserve Book | Library | Phase 3 | US-0407, US-0408 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Renew, reserve, queue and holds |  |  | 2026-09-20 | [5 empty] | Librarian | /school/library/reservations
SCR-205 | Fine / Lost / Damaged Book | Library | Phase 3 | US-0409, US-0410 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Collect, waive, bill; lost and damaged |  |  | 2026-09-20 | [5 empty] | Librarian | /school/library
SCR-206 | Digital Library | Library | Phase 3 | US-0411, US-0412 |  |  |  | Ready | In progress | In progress | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | A URL field only; no reader or entitlements |  |  | 2026-09-20 | [5 empty] | Librarian | /school/library/catalogue
SCR-207 | Library Reports | Library | Phase 3 | US-0413, US-0414 |  |  |  | Ready | In progress | In progress | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Stat tiles only; no date range or export |  |  | 2026-09-20 | [5 empty] | Librarian | /school/library
SCR-208 | Hostels / Buildings | Hostel | Phase 2 | US-0415, US-0416 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Hostel cards with kind, warden, fee, curfew |  |  | 2026-09-20 | [5 empty] | Hostel Warden | /school/hostel
SCR-209 | Rooms & Beds | Hostel | Phase 2 | US-0417, US-0418 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Rooms with bed count and occupancy grid |  |  | 2026-09-20 | [5 empty] | Hostel Warden | /school/hostel
SCR-210 | Student Hostel Allocation | Hostel | Phase 3 | US-0419, US-0420 |  |  |  | Ready | In progress | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Bed by bed only; no allocation register |  |  | 2026-09-20 | [5 empty] | Hostel Warden | /school/hostel
SCR-211 | Warden Management | Hostel | Phase 3 | US-0421, US-0422 |  |  |  | Ready | In progress | In progress | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Single warden field, no duty roster |  |  | 2026-09-20 | [5 empty] | Hostel Warden | /school/hostel
SCR-212 | Hostel Attendance | Hostel | Phase 3 | US-0423, US-0424 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Morning and night roll call |  |  | 2026-09-20 | [5 empty] | Hostel Warden | /school/hostel
SCR-213 | Leave / Outing | Hostel | Phase 3 | US-0425, US-0426 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Request, approve, signed out, returned |  |  | 2026-09-20 | [5 empty] | Hostel Warden | /school/hostel
SCR-214 | Mess / Meal Schedule | Hostel | Phase 3 | US-0427, US-0428 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Seven-day, four-meal editable grid |  |  | 2026-09-20 | [5 empty] | Hostel Warden | /school/hostel
SCR-215 | Hostel Complaints & Fees | Hostel | Phase 3 | US-0429, US-0430 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Complaints triage plus monthly hostel fees |  |  | 2026-09-20 | [5 empty] | Hostel Warden | /school/hostel
SCR-216 | Health Dashboard | Health / Counselling / Discipline | Phase 2 | US-0431, US-0432 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Five KPI cards with visits and alerts tabs |  |  | 2026-09-20 | [5 empty] | Nurse / Medical Officer | /school/health
SCR-217 | Student Medical Profile | Health / Counselling / Discipline | Phase 2 | US-0433, US-0434 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Profile, checkups, immunisations, visits |  |  | 2026-09-20 | [5 empty] | Nurse / Medical Officer | /school/health/students/[id]
SCR-218 | Clinic Visit | Health / Counselling / Discipline | Phase 2 | US-0435, US-0436 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Complaint, temperature, outcome, parent notice |  |  | 2026-09-20 | [5 empty] | Nurse / Medical Officer | /school/health
SCR-219 | Medication / First Aid | Health / Counselling / Discipline | Phase 3 | US-0437, US-0438 |  |  |  | Ready | In progress | In progress | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | One medicine field; no register or stock |  |  | 2026-09-20 | [5 empty] | Nurse / Medical Officer | /school/health
SCR-220 | Immunization / Allergy | Health / Counselling / Discipline | Phase 3 | US-0439, US-0440 |  |  |  | Ready | In progress | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Split across tabs; no drive or bulk entry |  |  | 2026-09-20 | [5 empty] | Nurse / Medical Officer | /school/health
SCR-221 | Counselling Appointments | Health / Counselling / Discipline | Phase 3 | US-0441, US-0442 |  |  |  | Ready | In progress | In progress | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Next-session date only; no booking diary |  |  | 2026-09-20 | [5 empty] | Nurse / Medical Officer | /school/counselling
SCR-222 | Counselling Case Notes | Health / Counselling / Discipline | Phase 3 | US-0443, US-0444 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Session notes with privacy and closure |  |  | 2026-09-20 | [5 empty] | Nurse / Medical Officer | /school/counselling
SCR-223 | Behaviour / Discipline Incidents | Health / Counselling / Discipline | Phase 3 | US-0445, US-0446 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Report incident with category and severity |  |  | 2026-09-20 | [5 empty] | Nurse / Medical Officer | /school/discipline
SCR-224 | Incident Action & Follow-up | Health / Counselling / Discipline | Phase 3 | US-0447, US-0448 |  |  |  | Ready | In progress | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | No way to mark an action served |  |  | 2026-09-20 | [5 empty] | Nurse / Medical Officer | /school/discipline
SCR-225 | Emergency Contacts & Escalation | Health / Counselling / Discipline | Phase 3 | US-0449, US-0450 |  |  |  | Ready | In progress | In progress | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Contacts shown; no escalation chain |  |  | 2026-09-20 | [5 empty] | Nurse / Medical Officer | /school/health
SCR-226 | Visitor Dashboard | Visitor / Gate / Security | Phase 2 | US-0451, US-0452 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Six stat cards including inside now |  |  | 2026-09-20 | [5 empty] | Security | /school/front-desk
SCR-227 | Visitor Check-in | Visitor / Gate / Security | Phase 2 | US-0453, US-0454 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Walk-in check-in with ID and host |  |  | 2026-09-20 | [5 empty] | Security | /school/front-desk
SCR-228 | Visitor Approval | Visitor / Gate / Security | Phase 2 | US-0455, US-0456 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Host confirms or declines an expected visitor |  |  | 2026-09-20 | [5 empty] | Security | /school/front-desk
SCR-229 | Visitor Pass | Visitor / Gate / Security | Phase 2 | US-0457, US-0458 |  |  |  | Ready | In progress | In progress | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Pass number shown, nothing printable |  |  | 2026-09-20 | [5 empty] | Security | /school/front-desk
SCR-230 | Visitor Check-out | Visitor / Gate / Security | Phase 3 | US-0459, US-0460 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Check out with minutes inside |  |  | 2026-09-20 | [5 empty] | Security | /school/front-desk
SCR-231 | Student Early Pickup / Gate Pass | Visitor / Gate / Security | Phase 3 | US-0461, US-0462 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Issue, approve, verify code, release |  |  | 2026-09-20 | [5 empty] | Security | /school/front-desk
SCR-232 | Staff & Vehicle Gate Log | Visitor / Gate / Security | Phase 3 | US-0463, US-0464 |  |  |  | Ready | In progress | In progress | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Vehicle captured; no staff gate log |  |  | 2026-09-20 | [5 empty] | Security | /school/front-desk
SCR-233 | Security Incident Log | Visitor / Gate / Security | Phase 3 | US-0465, US-0466 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Log with time, place, severity, closure |  |  | 2026-09-20 | [5 empty] | Security | /school/front-desk
SCR-234 | Inventory Dashboard | Inventory / Assets / Labs | Phase 2 | US-0467, US-0468 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Dashboard tiles, low stock, warranty list |  |  | 2026-09-20 | [5 empty] | Store Manager | /school/inventory
SCR-235 | Item Catalogue | Inventory / Assets / Labs | Phase 2 | US-0469, US-0470 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Item list, search, SKU, reorder level |  |  | 2026-09-20 | [5 empty] | Store Manager | /school/inventory
SCR-236 | Stock In / Purchase Receipt | Inventory / Assets / Labs | Phase 2 | US-0471, US-0472 |  |  |  | Ready | In progress | In progress | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | One item at a time; no multi-line receipt |  |  | 2026-09-20 | [5 empty] | Store Manager | /school/inventory
SCR-237 | Stock Issue / Return | Inventory / Assets / Labs | Phase 2 | US-0473, US-0474 |  |  |  | Ready | In progress | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Free-text issued-to; no requisition register |  |  | 2026-09-20 | [5 empty] | Store Manager | /school/inventory
SCR-238 | Supplier Management | Inventory / Assets / Labs | Phase 2 | US-0475, US-0476 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Supplier CRUD with contact and GSTIN |  |  | 2026-09-20 | [5 empty] | Store Manager | /school/inventory
SCR-239 | Asset Register | Inventory / Assets / Labs | Phase 2 | US-0477, US-0478 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Tag, serial, status, cost, warranty, history |  |  | 2026-09-20 | [5 empty] | Store Manager | /school/inventory
SCR-240 | Asset Assignment / Transfer | Inventory / Assets / Labs | Phase 3 | US-0479, US-0480 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Assignments tab: what is out and with whom |  |  | 2026-09-20 | [5 empty] | Store Manager | /school/inventory
SCR-241 | Asset Maintenance | Inventory / Assets / Labs | Phase 3 | US-0481, US-0482 |  |  |  | Ready | In progress | In progress | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Logs repairs; no schedule or AMC tracking |  |  | 2026-09-20 | [5 empty] | Store Manager | /school/inventory
SCR-242 | Lab Register | Inventory / Assets / Labs | Phase 3 | US-0483, US-0484 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Lab CRUD with room, subject, in-charge |  |  | 2026-09-20 | [5 empty] | Store Manager | /school/facilities
SCR-243 | Lab Equipment & Consumables | Inventory / Assets / Labs | Phase 3 | US-0485, US-0486 |  |  |  | Ready | In progress | Not started | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Equipment is free text; no items or stock |  |  | 2026-09-20 | [5 empty] | Store Manager | /school/facilities
SCR-244 | Practical / Lab Booking | Inventory / Assets / Labs | Phase 3 | US-0487, US-0488 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Period grid, book, cancel, my bookings |  |  | 2026-09-20 | [5 empty] | Store Manager | /school/facilities
SCR-245 | Stock & Asset Reports | Inventory / Assets / Labs | Phase 3 | US-0489, US-0490 |  |  |  | Ready | In progress | In progress | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Tiles and ledger; no date-range report |  |  | 2026-09-20 | [5 empty] | Store Manager | /school/inventory
SCR-246 | Events Calendar | Events / PTM / Communication | MVP | US-0491, US-0492 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Month grid and agenda across sources |  |  | 2026-09-20 | [5 empty] | School Admin | /school/calendar
SCR-247 | Create / Edit Event | Events / PTM / Communication | MVP | US-0493, US-0494 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Kind, dates, venue, audience, consent |  |  | 2026-09-20 | [5 empty] | School Admin | /school/events
SCR-248 | Event Details & Participants | Events / PTM / Communication | MVP | US-0495, US-0496 |  |  |  | Ready | In progress | In progress | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Consent roster only; no attendance |  |  | 2026-09-20 | [5 empty] | School Admin | /school/events
SCR-249 | Field Trip & Parent Consent | Events / PTM / Communication | Phase 2 | US-0497, US-0498 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Deadline and per-child consent with report |  |  | 2026-09-20 | [5 empty] | School Admin | /parent/events
SCR-250 | PTM Setup | Events / PTM / Communication | Phase 2 | US-0499, US-0500 |  |  |  | Ready | In progress | In progress | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Admin-only setup; teachers cannot create |  |  | 2026-09-20 | [5 empty] | Teacher | /school/ptm
SCR-251 | PTM Slot Booking | Events / PTM / Communication | Phase 2 | US-0501, US-0502 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Slot grid, book, cancel, mark done |  |  | 2026-09-20 | [5 empty] | Teacher | /parent/meetings
SCR-252 | Announcements | Events / PTM / Communication | Phase 2 | US-0503, US-0504 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Title, body, audience, attachment, send |  |  | 2026-09-20 | [5 empty] | School Admin | /school/notices
SCR-253 | Messaging / Inbox | Events / PTM / Communication | Phase 3 | US-0505, US-0506 |  |  |  | Ready | In progress | In progress | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Teacher and parent only; admin has no inbox |  |  | 2026-09-20 | [5 empty] | School Admin | /teacher/messages
SCR-254 | Notification Campaigns | Events / PTM / Communication | Phase 3 | US-0507, US-0508 |  |  |  | Ready | In progress | In progress | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | SMS and email skipped; schedule not wired |  |  | 2026-09-20 | [5 empty] | School Admin | /school/notices
SCR-255 | Communication History | Events / PTM / Communication | Phase 3 | US-0509, US-0510 |  |  |  | Ready | In progress | In progress | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Per-notice delivery only, no history log |  |  | 2026-09-20 | [5 empty] | School Admin | /school/notices
SCR-256 | Document Repository | Documents & Certificates | MVP | US-0511, US-0512 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Owner, category, verification and expiry |  |  | 2026-09-20 | [5 empty] | School Admin | /school/documents
SCR-257 | Student Documents | Documents & Certificates | MVP | US-0513, US-0514 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Expiring and unverified visible at a glance |  |  | 2026-09-20 | [5 empty] | School Admin | /school/documents/students
SCR-258 | Staff Documents | Documents & Certificates | Phase 2 | US-0515, US-0516 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Same view, filtered to staff |  |  | 2026-09-20 | [5 empty] | HR | /school/documents/staff
SCR-259 | Upload & Verification | Documents & Certificates | Phase 2 | US-0517, US-0518 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Upload, verify, reject with reason |  |  | 2026-09-20 | [5 empty] | School Admin | /school/documents
SCR-260 | Certificate Templates | Documents & Certificates | Phase 2 | US-0519, US-0520 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Six kinds with placeholders and serials |  |  | 2026-09-20 | [5 empty] | School Admin | /school/certificates/templates
SCR-261 | Generate Certificate | Documents & Certificates | Phase 3 | US-0521, US-0522 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Template and student with live preview |  |  | 2026-09-20 | [5 empty] | School Admin | /school/certificates
SCR-262 | Transfer Certificate | Documents & Certificates | Phase 3 | US-0523, US-0524 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Leaving date, conduct, dues check |  |  | 2026-09-20 | [5 empty] | School Admin | /school/certificates
SCR-263 | Certificate Register | Documents & Certificates | Phase 3 | US-0525, US-0526 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Serial, status, reprints, cancel |  |  | 2026-09-20 | [5 empty] | School Admin | /school/certificates
SCR-264 | Executive Analytics Dashboard | Reports & Analytics | MVP | US-0527, US-0528 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Headline tiles plus attendance and money trends, and the index of every report |  |  | 2026-09-20 | [5 empty] | School Admin | /school/reports
SCR-265 | Admission Reports | Reports & Analytics | MVP | US-0529, US-0530 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Funnel by stage with conversion rate |  |  | 2026-09-20 | [5 empty] | School Admin | /school/reports/admissions
SCR-266 | Student Strength Report | Reports & Analytics | MVP | US-0531, US-0532 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Class, section and capacity, with year on year |  |  | 2026-09-20 | [5 empty] | School Admin | /school/reports/strength
SCR-267 | Student Demographics | Reports & Analytics | MVP | US-0533, US-0534 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Gender, age and blood group, with how much is on file |  |  | 2026-09-20 | [5 empty] | School Admin | /school/reports/demographics
SCR-268 | Attendance Analytics | Reports & Analytics | Phase 2 | US-0535, US-0536 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Class and per-student percentages with CSV |  |  | 2026-09-20 | [5 empty] | School Admin | /school/reports/attendance
SCR-269 | Chronic Absenteeism Report | Reports & Analytics | Phase 2 | US-0537, US-0538 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | School-wide, with an adjustable threshold and CSV |  |  | 2026-09-20 | [5 empty] | School Admin | /school/reports/chronic-absence
SCR-270 | Academic Performance | Reports & Analytics | Phase 2 | US-0539, US-0540 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Whole-cohort analysis per exam |  |  | 2026-09-20 | [5 empty] | School Admin | /school/reports/exams
SCR-271 | Subject Performance | Reports & Analytics | Phase 2 | US-0541, US-0542 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Pass rate and average per subject, weakest first (in a tab, complete) |  |  | 2026-09-20 | [5 empty] | School Admin | /school/reports/exams
SCR-272 | Exam Result Analysis | Reports & Analytics | Phase 2 | US-0543, US-0544 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Pass rate tile and grade ring (in a tab, complete) |  |  | 2026-09-20 | [5 empty] | School Admin | /school/reports/exams
SCR-273 | Fee Collection Report | Reports & Analytics | Phase 2 | US-0545, US-0546 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | By head, class, mode and month, with CSV |  |  | 2026-09-20 | [5 empty] | School Admin | /school/reports/fee-collection
SCR-274 | Outstanding Dues Report | Reports & Analytics | Phase 3 | US-0547, US-0548 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Five ageing buckets and the defaulter list, with CSV |  |  | 2026-09-20 | [5 empty] | School Admin | /school/reports/dues
SCR-275 | Finance Summary | Reports & Analytics | Phase 3 | US-0549, US-0550 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Cash book tab; no profit and loss view (in a tab, complete) |  |  | 2026-09-20 | [5 empty] | School Admin | /school/accounts
SCR-276 | Staff Attendance Report | Reports & Analytics | Phase 3 | US-0551, US-0552 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | A month per person, holidays excluded |  |  | 2026-09-20 | [5 empty] | School Admin | /school/reports/staff-attendance
SCR-277 | Payroll Summary | Reports & Analytics | Phase 3 | US-0553, US-0554 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Per-run totals and bank file (in a tab, complete) |  |  | 2026-09-20 | [5 empty] | School Admin | /school/payroll
SCR-278 | Teacher Performance | Reports & Analytics | Phase 3 | US-0555, US-0556 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Counts of work done, stated as not a ranking |  |  | 2026-09-20 | [5 empty] | School Admin | /school/reports/teachers
SCR-279 | Transport Utilization | Reports & Analytics | Phase 3 | US-0557, US-0558 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Riders against seats, over-capacity routes flagged |  |  | 2026-09-20 | [5 empty] | School Admin | /school/reports/transport
SCR-280 | Library Usage | Reports & Analytics | Phase 3 | US-0559, US-0560 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Issues and returns by month, and top titles |  |  | 2026-09-20 | [5 empty] | School Admin | /school/reports/library
SCR-281 | Inventory & Asset Report | Reports & Analytics | Phase 3 | US-0561, US-0562 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Stock and asset value by category, and low stock |  |  | 2026-09-20 | [5 empty] | School Admin | /school/reports/inventory
SCR-282 | Communication / Notification Report | Reports & Analytics | Phase 3 | US-0563, US-0564 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | By audience, month and channel, skipped kept apart from failed |  |  | 2026-09-20 | [5 empty] | School Admin | /school/reports/notifications
SCR-283 | Custom Report Builder | Reports & Analytics | Phase 3 | US-0565, US-0566 |  |  |  | Ready | In progress | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Sources, columns, run and export; no filter UI |  |  | 2026-09-20 | [5 empty] | School Admin | /school/data-desk
SCR-284 | User Management | Settings / Roles / Permissions / Audit | MVP | US-0567, US-0568 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Create login, activate, reset password |  |  | 2026-09-20 | [5 empty] | IT Admin | /school/staff
SCR-285 | Roles | Settings / Roles / Permissions / Audit | MVP | US-0569, US-0570 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Role CRUD with built-in and custom |  |  | 2026-09-20 | [5 empty] | IT Admin | /school/roles
SCR-286 | Permissions | Settings / Roles / Permissions / Audit | MVP | US-0571, US-0572 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Permission catalogue only inside the role modal (in a tab, complete) |  |  | 2026-09-20 | [5 empty] | IT Admin | /school/roles
SCR-287 | Role Permission Matrix | Settings / Roles / Permissions / Audit | MVP | US-0573, US-0574 |  |  |  | Ready | In progress | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Per-role grid, no cross-role matrix |  |  | 2026-09-20 | [5 empty] | IT Admin | /school/roles
SCR-288 | User Role Assignment | Settings / Roles / Permissions / Audit | MVP | US-0575, US-0576 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Assign person, role and branch |  |  | 2026-09-20 | [5 empty] | IT Admin | /school/roles
SCR-289 | School Settings | Settings / Roles / Permissions / Audit | Phase 2 | US-0577, US-0578 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Settings index with set-up state |  |  | 2026-09-20 | [5 empty] | IT Admin | /school/settings
SCR-290 | Academic Settings | Settings / Roles / Permissions / Audit | Phase 2 | US-0579, US-0580 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Grade scales and report-card settings |  |  | 2026-09-20 | [5 empty] | IT Admin | /school/grading
SCR-291 | Notification Settings | Settings / Roles / Permissions / Audit | Phase 2 | US-0581, US-0582 |  |  |  | Ready | Not started | Not started | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | No notification channel or template settings |  |  | 2026-09-20 | [5 empty] | IT Admin | -
SCR-292 | Integration / API Settings | Settings / Roles / Permissions / Audit | Phase 3 | US-0583, US-0584 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Outside services and whether they are connected |  |  | 2026-09-20 | [5 empty] | IT Admin | /school/settings
SCR-293 | Security & Password Policy | Settings / Roles / Permissions / Audit | Phase 3 | US-0585, US-0586 |  |  |  | Ready | Not started | Not started | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | No password policy anywhere |  |  | 2026-09-20 | [5 empty] | IT Admin | -
SCR-294 | Audit Logs | Settings / Roles / Permissions / Audit | Phase 3 | US-0587, US-0588 |  |  |  | Ready | Done | Done | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Filtered list with CSV export |  |  | 2026-09-20 | [5 empty] | IT Admin | /school/audit-log
SCR-295 | Data Import / Export / Backup | Settings / Roles / Permissions / Audit | Phase 3 | US-0589, US-0590 |  |  |  | Ready | Done | In progress | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Import and export done; no backup or restore |  |  | 2026-09-20 | [5 empty] | IT Admin | /school/data-desk
SCR-296 | Notification Center | Events / PTM / Communication | MVP | US-0591, US-0592 |  |  |  | Ready | In progress | In progress | Not assessed | Not assessed | Not assessed |  | Not scheduled |  | Parents only; staff have no inbox page |  |  | 2026-09-20 | [5 empty] | All Users | /parent/notices

## Shared Work
Shared development work
Proposed cross-screen backlog. Confirm applicability. These items are separate from the 296-screen count.
Done requires an owner, evidence and no blocker. Use Not required only with a reason in the evidence field.
Work ID | Shared deliverable | Owner | Sprint | Due date | Status | Blocker / dependency | Evidence / reason | Next action | Verified | Schedule
SH-001 | Development and staging environments |  |  |  | Not assessed
SH-002 | Database schema and migrations |  |  |  | Not assessed
SH-003 | Authentication and session management |  |  |  | Not assessed
SH-004 | Role and permission enforcement |  |  |  | Not assessed
SH-005 | School / tenant data isolation |  |  |  | Not assessed
SH-006 | Shared UI components and routing |  |  |  | Not assessed
SH-007 | File upload and document storage |  |  |  | Not assessed
SH-008 | Notification delivery integration |  |  |  | Not assessed
SH-009 | Payment provider integration |  |  |  | Not assessed
SH-010 | Background jobs and scheduled work |  |  |  | Not assessed
SH-011 | Report and export services |  |  |  | Not assessed
SH-012 | Automated test framework |  |  |  | Not assessed
SH-013 | Logging, monitoring and error handling |  |  |  | Not assessed
SH-014 | Backup and restore validation |  |  |  | Not assessed
SH-015 | Responsive and accessibility checks |  |  |  | Not assessed
SH-016 | Deployment pipeline and release checks |  |  |  | Not assessed